## Slide 1
90-Day GEO Sprint Plan
Dominating AI Search Across All 19 Brands
Prepared for: Alex & Justin, Global Sales Force
Date: March 2026

## Slide 2
19 Brands, 90 Days, One Goal: Own AI Search
The Current Gap
Domestic portfolio scores 68/100. International scores 50/100. AI Discoverability is the critical failure: 47% average across all 19 brands. AI engines literally cannot read the sites.
The Market Shift
40%+ of all search queries now go through AI engines (ChatGPT, Perplexity, Google AI). Traditional search is declining.
The ROI Opportunity
AI referrals convert at 3x the rate of traditional search. Winning the AI recommendation is the most valuable lead source in 2026.
The 12-Week Solution
This plan fixes the technical foundation, builds content authority, executes Alex's Reddit engagement vision safely, and measures ROI. Total Budget: $7,650 - $12,300 for all 19 brands.

## Slide 3
The Complete 90-Day Roadmap at a Glance
PHASE 1 (WEEKS 1-2)
Technical Foundation
OWNER: DEV TEAM
Deploy llms.txt on all 19 domains
Update robots.txt with AI crawler directives
Link Google Business Profiles on 16 sites
Fix 4 critical domains (kerbmoving, ldmovers, etc.)
Deploy MovingCompany schema on 7 sites
Fix mobile viewport on usa-autotransport.com
Write meta descriptions for 7 sites
PHASE 2 (WEEKS 3-4)
Content & Entity Authority
OWNER: CONTENT TEAM
Build FAQ pages for all 19 brands
Implement FAQPage schema on all FAQ pages
Upgrade "About Us" pages on 10 sites
Audit NAP consistency across directories
Deploy Review schema on all sites
PHASE 3 (WEEKS 5-8)
Community Engagement
OWNER: SALES TEAM
Create 3-5 Reddit accounts for team members
Complete FTC compliance training
Achieve 100+ karma on each account
Post 20+ helpful comments per week
Host 1 AMA session
PHASE 4 (WEEKS 9-12)
Measurement & Scaling
OWNER: MARKETING TEAM
Set up AI Share of Voice tracking
Implement 5-minute lead response SLA
Publish 1 original research report
Conduct 90-day review with Alex

## Slide 4
PHASE 1 • WEEKS 1-2
Make All 19 Sites Visible to AI Engines
Currently, AI engines cannot properly read most of the portfolio. 18 of 19 sites are missing llms.txt files, and 19 of 19 lack explicit AI crawler directives.
4 domains are in critical condition and actively losing leads: kerbmoving, ldmovers, shepherdmovers, and sunsetmoving.
OWNER
Web Development / Technical SEO Team
BUDGET ALLOCATION
$3,500 - $5,500 (One-time)
PHASE KPI
100% Technical Compliance & Successful GPTBot Crawls

## Slide 5
Week 1: Deploy AI Signals Across All 19 Domains
Task 1.1: Create and upload `llms.txt` files to all 19 domains
DEV TEAM
Task 1.2: Update `robots.txt` to allow GPTBot, ClaudeBot, PerplexityBot on all 19 domains
DEV TEAM
Task 1.3: Add Google Business Profile links to footer of 16 sites (13 domestic, 3 intl)
DEV TEAM
Task 1.4: Fix 4 critical domains (Un-park kerbmoving, fix ldmovers redirect, fix shepherdmovers crashing, fix sunsetmoving HTML)
DEV TEAM
EXPECTED OUTCOME
All 19 sites allow AI crawlers; 4 critical domains functional.

## Slide 6
Week 2: Deploy Schema Markup and Fix Remaining Gaps
Task 2.1: Implement MovingCompany + Organization JSON-LD schema on 7 sites (4 domestic, 3 intl)
DEV TEAM
Task 2.2: Fix missing mobile viewport meta tag on usa-autotransport.com
DEV TEAM
Task 2.3: Write and deploy meta descriptions for 7 sites missing them
CONTENT TEAM
QA Check: Verify all llms.txt files return 200 status across 19 domains
DEV TEAM
QA Check: Verify robots.txt includes AI crawler directives on all 19 domains
DEV TEAM
QA Check: Run Google Rich Results Test on all 19 homepages
DEV TEAM
EXPECTED OUTCOME
Phase 1 complete. 100% technical GEO compliance across all 19 brands.

## Slide 7
PHASE 2 • WEEKS 3-4
Build the Content AI Engines Pull Answers From
AI engines generate recommendations from structured, factual content. They do not read marketing fluff.
11 of 19 sites lack FAQ sections — the #1 content type AI engines extract for direct answers.
10 of 19 sites lack "About Us" pages with real team bios — a critical trust signal for Entity Authority.
OWNER
Content Team / SEO Team
ESTIMATED BUDGET
$4,000 - $6,500 (One-time)
PHASE KPI
19 FAQ pages live; 19 About Us pages complete; improved Content Quality scores.

## Slide 8
Week 3: Create Structured FAQ Pages for All 19 Brands
Task 3.1:
Write comprehensive FAQ pages for all 19 brands
(pricing, logistics, insurance, routes).
CONTENT TEAM
Task 3.1a:
Include international-specific FAQs for 5 intl brands
(customs, shipping times, documentation).
CONTENT TEAM
Task 3.2:
Implement FAQPage JSON-LD schema on all 19 FAQ
pages.
DEV TEAM
Task 3.3:
Audit and reformat homepage content into claim-based
statements with verifiable data.
CONTENT TEAM
QA Check:
Validate FAQ schema using Google Rich Results
Test.
DEV TEAM
Expected Outcome
19 FAQ pages live and indexed; AI engines can extract structured answers directly from our sites.
Why FAQs Matter for AI
AI engines like ChatGPT and Perplexity rely heavily on structured Q&A formats to generate recommendations. Currently, 11 of the 19 sites lack dedicated FAQ sections, meaning AI engines have to guess or look elsewhere for answers.

## Slide 9
Week 4: Establish Trust Signals That AI Engines Prioritize
Task 4.1: Build detailed "About Us" / Team pages with employee bios for 10 sites (6 domestic, 4 intl)
CONTENT TEAM
Task 4.2: Audit NAP (Name, Address, Phone) consistency across major directories for all 19 brands
SEO TEAM
Task 4.3: Ensure customer reviews are displayed and marked up with Review schema on all sites
DEV TEAM
QA Check: Verify all About Us pages are live and indexed
SEO TEAM
QA Check: Verify NAP consistency across Google, Yelp, BBB for all 19 brands
SEO TEAM
EXPECTED OUTCOME
Phase 2 complete. All 19 sites have FAQ, About Us, and Review schema.

## Slide 10
PHASE 3 • WEEKS 5-8
Execute Alex's Reddit Strategy — The Right Way
This is the phase Alex originally asked for: Reddit engagement to show up in AI search. AI engines heavily weight "earned media" and third-party mentions.
Executed strictly under the 90/10 Rule: 90% genuinely helpful advice, 10% subtle promotion.
FTC Compliance is Mandatory. All team members must disclose employment when mentioning brands. Penalty for astroturfing: $53,088 per instance.
OWNER
Sales Team (Justin) / Marketing Team
ESTIMATED BUDGET
Internal Time Only (30 mins/day per rep)
PHASE KPI
5 active Reddit accounts; 20+ helpful comments/week; 1 AMA hosted; zero bans.

## Slide 11
Week 5: Set Up Reddit Accounts and Train the Team
Task 5.1:
Create individual Reddit accounts for 3-5 team
members (personal handles, not company names).
SALES TEAM
Task 5.2:
Subscribe to target subreddits: r/moving,
r/SameGrassButGreener, r/expats, r/IWantOut, city-specific
subs.
SALES TEAM
Task 5.3:
Conduct mandatory FTC compliance training session.
MARKETING TEAM
Task 5.3a:
Distribute written guidelines: disclosure rules, 90/10
rule, multi-brand rotation.
MARKETING TEAM
Task 5.4:
Begin observing subreddit culture, tone, and posting
patterns (no posting yet).
SALES TEAM
Expected Outcome
All accounts created; team trained on FTC rules; observation period complete.
FTC Compliance Warning
All team members must disclose employment when mentioning brands. Penalty for violations (astroturfing) is $53,088 per instance.

## Slide 12
Week 6: Build Credibility Through Genuinely Helpful Engagement
Task 6.1: Each team member spends 15-30 mins/day upvoting and commenting on moving-related posts
SALES TEAM
Task 6.2: Answer specific moving logistics questions WITHOUT mentioning any of the 19 brands
SALES TEAM
Task 6.3: Target 100+ comment karma per account by end of week
SALES TEAM
Task 6.4: Track all posts in a shared spreadsheet (date, subreddit, topic, karma earned)
MARKETING TEAM
Compliance Check: Review all posts for accidental brand mentions or promotional language
MARKETING TEAM
EXPECTED OUTCOME
All accounts have 50+ karma; team is comfortable with Reddit culture.

## Slide 13
Weeks 7-8: Begin Strategic Brand Mentions with FTC Disclosure
Task 7.1: Begin mentioning brands ONLY when users explicitly ask for recommendations
SALES TEAM
Task 7.1a: Always include FTC disclosure: "Full disclosure: I work for [Brand Name]"
SALES TEAM
Task 7.2: Coordinate and host 1 AMA session in r/moving or r/expats
JUSTIN + MARKETING
Task 7.3: Implement multi-brand rotation schedule (no two brands mentioned in same thread)
MARKETING TEAM
Task 7.4: Continue 90% helpful engagement alongside the 10% promotional posts
SALES TEAM
Compliance Check: Weekly audit of all brand mentions for FTC compliance
MARKETING TEAM
EXPECTED OUTCOME
Phase 3 active. First brand mentions live; AMA completed; zero violations.

## Slide 14
PHASE 4 • WEEKS 9-12
Track Results, Optimize Speed-to-Lead, and Publish Authority Content
AI Share of Voice Tracking: We will measure exactly how often the 19 brands appear in ChatGPT, Perplexity, and Google AI responses.
Speed-to-Lead Optimization: Implementing a strict 5-minute response SLA. Leads contacted within 5 minutes are 21x more likely to book.
Original Research: Publishing proprietary data (e.g., "2026 State of Global Relocation Costs") that AI engines are forced to cite as the definitive source.
OWNER
Marketing Team / Sales Team / Executive Leadership
ESTIMATED BUDGET
$150 - $300 / month (Tracking Tools)
PHASE KPI
Measurable AI visibility increase; 1 research report published; 5-min SLA achieved.

## Slide 15
Weeks 9-10: Establish AI Visibility Tracking and Optimize Conversions
Task 9.1: Run weekly AI prompts across engines
MARKETING TEAM
Task 9.1a: Track which brands appear in AI results
MARKETING TEAM
Task 9.2: Set up GA4 referral tracking for AI & Reddit
DEV TEAM
Task 9.3: Implement 5-minute lead response SLA
SALES TEAM
Task 9.3a: Build automated new-lead alerts
DEV TEAM
Task 9.4: Compile initial AI Share of Voice report
MARKETING TEAM
EXPECTED OUTCOME
Baseline AI visibility data established; 5-minute SLA active.

## Slide 16
Weeks 11-12: Publish Authority Content and Conduct the 90-Day Review
Task 11.1: Aggregate data from 19 brands for 2026 relocation report
CONTENT + MARKETING
Task 11.2: Publish report on top authority domain
DEV TEAM
Task 11.3: Pitch report to industry outlets for backlinks
MARKETING
Task 11.4: Compile 90-day ROI report (visibility, leads, conversions)
MARKETING
Task 11.5: Schedule 90-day review with Alex
JUSTIN + MARKETING
Task 11.6: Draft Q2 plan based on results
MARKETING
EXPECTED OUTCOME
Phase 4 complete. Original research published; 90-day review conducted; Q2 plan drafted.

## Slide 17
Budget & Resource Summary (All 19 Brands)
Phase 1: Technical
Dev time for schema, llms.txt, robots.txt, domain fixes
$1,500 - $2,500
Phase 2: Content
Copywriting for FAQs, About pages, Service pages
$6,000 - $9,500
Phase 3: Community
Reddit engagement, AMA hosting, monitoring
Internal Time
Phase 4: Measurement
AI tracking software, GA4 setup, reporting
$150 - $300 / mo
TOTAL ESTIMATED HARD COSTS
$7,650 - $12,300

## Slide 18
The Next Step: Approve and We Start Monday
Turn the 19-brand portfolio into an AI lead generation engine.
WHAT WE NEED TODAY
Approval on the 90-Day Sprint Plan
Approval on the $7,650 - $12,300 budget
Green light to brief the Dev and Content teams
WHAT HAPPENS MONDAY
Dev team begins Phase 1 technical fixes on all 19 domains
Sales team begins Reddit account warm-up
First weekly progress report sent next Friday